## Tasks
Number	Dependencies	Status	Venue	Type	Priority level	Description	Notes
1		C	DB Construction	Design	High	Schema for database	doc/ER_diagram.dia (requires Dia program), sql/db_tables.sql, and sql/db_constraints.sql
2		C	DB Construction	Data	High	Filling movie table.	scripts/movie and bin/movie2sql (from src/movie2sql.c) creates sql/movie.sql
4		C	DB Construction	Data	High	Filling crewperson table.	data/crewprson.txt, scripts/crewperson, bin/crew2sql (from src/crew2sql.hs), and bin/nameFormatter (from src/nameFormatter.hs) creates sql/crewperson.sql
5		C	DB Construction	Data	High	Filling country table.	data/country.txt, scripts/country, and bin/country2sql (from src/country2sql.hs) creates sql/country.sql
6		C	DB Construction	Data	High	Filling oscar table.	data/oscar.txt, src/oscar2sql.hs, bin/oscar2sql, and sql/oscar.sql
7		C	DB Construction	Data	High	Filling oscargivento table.
8	26	B	DB Construction	Data	High	Filling list table.
9	26	B	DB Construction	Data	High	Filling list_contains table.
10		C	DB Construction	Data	High	Filling genre table.	data/genre.txt, sql/genre.sql, src/genre2sql.hs, and bin/genre2sql.
11		IP	DB Construction	Data	High	Filling tagged_to table.	changed from genre_contains
12	67	IP	DB Construction	Data	High	Filling worked_on table.	some data already created from oscars. Need another script/program to read filmographies
13		F	DB Construction	Bug	Low	movie.sql always results in the last movie appearing twice (although, Postgres will take care of this, I think, by rejecting the second one)
14		F	DB Construction	Bug	Low	movie table's year_constraint is hard-coded as <= 2012, for example. is there a way to make this dynamic? (some sql current_year function + 3, maybe?)	Will have front-end take care of this.
15		F	DB Construction	Bug	Medium	'&frac12' should not be stored in the database for the '½' character—let the php or javascript, or whatever take care of the translation.	this was taken care of with task #22
16		C	GUI	Design	Medium	Create a FiLTH logo.	images/filth_logo.png
17		D	Web Development	Feature	Low	Add <!DOCTYPE at top of web pages.
18		D	Web Development	Feature	Low	Create stylesheet(s) for the site.
19		R	Web Development	Feature	Nice-to-have	Titles of movies from search results are links to imdb (example: http://www.imdb.com/find?s=titles&q=the+shawshank+redemption)
20		C	DB Construction	Option	Low	Combine db_*.sql files into one sql file and name it something like setup_database.sql or init_database.sql.
21		NS	Web Development	Design	Nice-to-have	Create a background image.
22		C	DB Construction	Design	Medium	Change limited domains (such as movie.mystarrating, oscargivento.status) to smallint type (front-end can then translate accordingly)
23		C	DB Construction	Design	Medium	Change naming convention of tables, etc. to words seperated by underscore
24		D	DB Construction	Design	High	Change db schema to a more dimensional model—have movie table contain all attributes with foreign keys to other tables (maybe not entirely)
25		D	GUI	Design	Low	Go through tutorials on Java GUIs with NetBeans, wxPython, QtCreator, etc.
26		IP	DB Construction	Data	Medium	Gather up list data and type them up in a certain format for a program to easily parse through to convert to sql to dump into db
27		F	DB Construction	Bug	High	“A Dog's Life” and “A Day's Pleasure” have 'A' as 'a' (not capitalized). They are both shorts.
28		C	DB Construction	Design	High	Titles shouldn't have “[short]” in them. Let there be a “Short” genre to take care of that.	this is taken care of on the genre side—just needs to be fixed in movie2sql
29	67	NS	DB Construction	Data	Medium	Filling movie table with movies haven't seen.	need to work on filmographies
30		C	DB Construction	Design	Medium	Don't contain accented special characters. They will not be found when searching (e.g. Penélope Cruz vs. Penelope Cruz).
31		C	DB Construction	Option	High	Rewrite movie2sql in Python (and to take care of #27 and #28)	src/movie2sql.py
32		C	DB Construction	Design	Low	sql files for both postgres and mysql (mysql workbench needs the database name, pgAdminIII doesn't)
33		C	DB Construction	Design	Medium	add schemas for my movie awards
34		D	Development		Low	Create a Redmine instance for this project
35		C	Research		Low	Learn LaTeX	This is in order to insert a movie automatically into a LaTeX file that creates a document like Movie_Ratings.doc, for example, and the lists that the DB will have data for.
36		C	DB Construction	Design	Low	Add comments attribute of type TEXT to the movie table
37		NS	DB Construction	Design	Low	Add indexes to certain attributes? Research which ones should be.	Maybe save this for last. Gather stats on query execution times for various indexes once all of the data in populated.
38		B	Research		Medium	Implement text search	Wait until development environment is set-up and MVC is in place and working
39		NS	Development		Low	Type up old lists of my awards
40		C	Development		Medium	Write up my movie rating list in LaTex.	This will then be used in FiLTH when adding a movie seen—it will add it to the LaTex file as well as the database and produce a new pdf for the movie rating list.
41		C	DB Construction	Design	High	Remove country table and use encoding scheme like star_rating where front-end takes care of the translation and document the encoding in init_....sql	This will at least remove one join
42		NS	Development		Medium	Insert copyright headers for all source files and add a COPYING file	most likely GPLv3
43		D	Research		Low	Learn sqlite
44		NS	DB Construction	Data	Low	Use NULL in the mpaa column for movies released before the MPAA rating system?	Would require adding some code to the movie2sql.py script
45		C	Development		Medium	Add echoes to drop_and_create scripts and use a switch for psql to redirect error/notice messages to the temp files
46		F	DB Construction	Bug	Low	M*A*S*H is being inserted as M2A2S2H ?
47		NS	DB Construction	Data	Low	Allow accented characters back into the database ?	fine for crewPerson names, but would have to go in to Movie_Ratings.doc and add them all in manually.
48		D	GUI	Design	Medium	Learn QtCreator
49		C	Development		Medium	Write a script to just drop and add the movie table not the whole database
50		C	DB Construction	Data	Medium	Add documentaries (features) to Oscar data
51		C	Development		Medium	Write parser for Movie_Ratings	mrp.py in progress
52		F	DB Construction	Bug	High	oscarGivenTo.sh not extracting screenplay nominations from 1929 and 1930	just add a “Screenplay” category to oscar table
53		C	DB Construction	Design	High	change movie schema to have country as text rather than smallint
54		F	DB Construction	Bug	Medium	The dummy Battle of Algiers record is being inserted into the database even for movie additions
55		C	DB Construction		Medium	move some of the special case handling (names, for example) in OscarParser to the oscar_given_to.sh script
56		C	Development		Low	clean up OscarParser code
57		C	DB Construction		Medium	add smallint/tinyint attribute “shared” in oscar_given_to table indicating how many other recipients the nominee is sharing the award with
58		C	DB Construction		Low	Update scripts to execute all movieN.sql and crew_personN.sql files (drop_and... scripts, and update_movie_table script)	or just concat all of them together...
59		C	DB Construction		Medium	Add code to OscarParser to write sql inserts for the worked_on table since the information is there anyway
60		NS	DB Construction		Low	Create separate db schemas (one for performance, one for space, and one for both possibly) and try out the query speeds and check db sizes
61		NS	DB Construction		Low	Create init_sqlite_database.sql
62		IP	Development		High	Setup dev environment for Spring, Hibernate, ant, Apache, tomcat, Freemarker
62a		C	Development		High	setup Apache 2.4
62b		IP	Development		High	setup Spring 3.1	downloaded and extracted to workspace, included jar files in eclipse project—could probably delete everything else and just move those jars into FiLTH/jar
62c		IP	Development		High	setup Hibernate	downloaded and extracted to workspace, included jar files in eclipse project—could probably delete everything else and just move those jars into FiLTH/jar
62d		C	Development		High	setup ant 1.8.4
62e		C	Development		High	setup tomcat	downloaded and extracted
62f		IP	Development		High	setup Freemarker	downloaded and placed jar into FiLTH/jar
63		R	Development		Medium	Refactor tickets into agile-style project development / find an application for this kind of project management (Rally, FogBugz, etc)	Have stories with subtasks, spike stories, proposals (or, rather, results of research). Directory hierarchy in /doc (/doc/stories, /doc/research_reports, etc)
64		NS	DB Construction		Low	Use SQL TRUNCATE where appropriate in db scripts
65		NS	Development		High	Make movie.sh require db name and password (so as to not hard-code them in models.py, and can then unignore model.py in .gitignore)
66	62	NS	Development		Medium	Replace Python/SQLAlchemy with Java/Hibernate
67	51	NS	DB Construction		Medium	Write a script to convert Filmographies to sql for worked_on table (after parsing)	awk?
68		C	DB Construction		High	Change genre table to tag table	Entails changing the genre.py script, models.py, genre.sql, genre_contains.sql, and most likely starting the script over from the beginning
69		C	Development		High	Add catch of all exceptions in movie2sql.py, spit out the stack trace to a log file, return non-0 number to shell, and have movie.sh check return value and replace previous_movie_ratings with the backup if movie2sql.py failed
70		NS	DB Construction		Low	Create a filth user, and a filth-admin user
71		NS	Development		Medium	Create a more agile environement (see IDEAS section of NOTES)

## Status Legend
C	Completed
IP	In Progess
NS	Not Started
F	Fixed
D	Dismissed
R	Researching
B	Blocked