## Tasks
Number	Dependencies	Status	Venue	Type	Priority level	Description	Notes
1		C	DB Construction	Design	High	Schema for database	doc/ER_diagram.dia (requires Dia program), sql/db_tables.sql, and sql/db_constraints.sql
2		C	DB Construction	Feature	High	Filling movie table.	scripts/movie and bin/movie2sql (from src/movie2sql.c) creates sql/movie.sql
4		C	DB Construction	Feature	High	Filling crewperson table.	data/crewprson.txt, scripts/crewperson, bin/crew2sql (from src/crew2sql.hs), and bin/nameFormatter (from src/nameFormatter.hs) creates sql/crewperson.sql
5		C	DB Construction	Feature	High	Filling country table.	data/country.txt, scripts/country, and bin/country2sql (from src/country2sql.hs) creates sql/country.sql
6		C	DB Construction	Feature	High	Filling oscar table.	data/oscar.txt, src/oscar2sql.hs, bin/oscar2sql, and sql/oscar.sql
7		IP	DB Construction	Feature	High	Filling oscargivento table.
8	26	NS	DB Construction	Feature	High	Filling list table.
9	26	NS	DB Construction	Feature	High	Filling listcontains table.
10		C	DB Construction	Feature	High	Filling genre table.	data/genre.txt, sql/genre.sql, src/genre2sql.hs, and bin/genre2sql.
11		NS	DB Construction	Feature	High	Filling genrecontains table.
12		NS	DB Construction	Feature	High	Filling workedon table.
13		NS	DB Construction	Bug	Low	movie.sql always results in the last movie appearing twice (although, Postgres will take care of this, I think, by rejecting the second one)
14		NS	DB Construction	Bug	Low	movie table's year_constraint is hard-coded as <= 2012, for example. is there a way to make this dynamic? (some sql current_year function + 3, maybe?)
15		C	DB Construction	Bug	Medium	'&frac12' should not be stored in the database for the '½' character—let the php or javascript, or whatever take care of the translation.	this was taken care of with task #22
16		C	GUI	Design	Medium	Create a FiLTH logo.	images/filth_logo.png
17		NS	Web Development	Feature	Low	Add <!DOCTYPE at top of web pages.
18		NS	Web Development	Feature	Medium	Create stylesheet(s) for the site.
19		NS	Web Development	Feature	Low	Titles of movies from search results are links to imdb (example: http://www.imdb.com/find?s=titles&q=the+shawshank+redemption)
20		C	DB Construction	Option	Low	Combine db_*.sql files into one sql file and name it something like setup_database.sql or init_database.sql.
21		NS	Web Development	Design	Low	Create a background image.
22		C	DB Construction	Design	Medium	Change limited domains (such as movie.mystarrating, oscargivento.status) to smallint type (front-end can then translate accordingly)
23		C	DB Construction	Design	Medium	Change naming convention of tables, etc. to words seperated by underscore
24		D	DB Construction	Design	High	Change db schema to a more dimensional model—have movie table contain all attributes with foreign keys to other tables (maybe not entirely)
25		IP	GUI	Design	High	Go through tutorial on Java GUIs with NetBeans / wxPython
26		NS	DB Construction	Feature	Medium	Gather up list data and type them up in a certain format for a program to easily parse through to convert to sql
27		NS	DB Construction	Bug	High	“A Dog's Life” and “A Day's Pleasure” have 'A' as 'a' (not capitalized). They are both shorts.
28		NS	DB Construction	Design	High	Titles shouldn't have “[short]” in them. Let there be a “Short” genre to take care of that.	this is taken care of on the genre side—just needs to be fixed in movie2sql
29		NS	DB Construction	Feature	Medium	Filling movie table with movies haven't seen.
30		C	DB Construction	Design	Medium	Don't contain accented special characters. They will not be found when searching (e.g. Penélope Cruz vs. Penelope Cruz).
31		IP	DB Construction	Option	High	Rewrite movie2sql in Python (and to take care of #27 and #28)