## Sheet1
Number	Status	Venue	Type	Priority level	Description	Notes
1	C	DB Construction	Design	High	Schema for database	doc/ER_diagram.dia (requires Dia program), sql/db_tables.sql, and sql/db_constraints.sql
2	C	DB Construction	Feature	High	Filling movie table.	scripts/movie and bin/movie2sql (from src/movie2sql.c) creates sql/movie.sql
4	C	DB Construction	Feature	High	Filling crewperson table.	data/crewprson.txt, scripts/crewperson, bin/crew2sql (from src/crew2sql.hs), and bin/nameFormatter (from src/nameFormatter.hs) creates sql/crewperson.sql
5	C	DB Construction	Feature	High	Filling country table.	data/country.txt, scripts/country, and bin/country2sql (from src/country2sql.hs) creates sql/country.sql
6	IP	DB Construction	Feature	High	Filling oscar table.
7	IP	DB Construction	Feature	High	Filling oscargivento table.
8	NS	DB Construction	Feature	High	Filling list table.
9	NS	DB Construction	Feature	High	Filling listcontains table.
10	NS	DB Construction	Feature	High	Filling genre table.
11	NS	DB Construction	Feature	High	Filling genrecontains table.
12	NS	DB Construction	Feature	High	Filling workedon table.
13	NS	DB Construction	Bug	Low	movie.sql always results in the last movie appearing twice (although, Postgres will take care of this, I think, by rejecting the second one)
14	NS	DB Construction	Bug	Low	movie table's year_constraint is hard-coded as <= 2012, for example. is there a way to make this dynamic? (some sql current_year function + 3, maybe?)
15	NS	DB Construction	Bug	Medium	'&frac12' should not be stored in the database for the '½' character—let the php or javascript, or whatever take care of the translation.
16	NS	Interface	Design	Medium	Create a FiLTH logo and background image.
17	NS	Web Development	Feature	Low	Add <!DOCTYPE at top of web pages.
18	NS	Web Development	Feature	Medium	Create stylesheet(s) for the site.
19	NS	Web Development	Feature	Low	Titles of movies from search results are links to imdb (example: http://www.imdb.com/find?s=titles&q=the+shawshank+redemption)
20	NS	DB Construction	Option	Low	Combine db_*.sql files into one sql file and name it something like setup_database.sql or init_database.sql.